{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Feuil1","Feuil2","Feuil3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Feuil1","index":0,"n_rows":50,"n_cols":22,"rows_kept":50,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Order Nr","Title","Status","Launched by","Topic","Ressources","Status Date","Action Pilot","FA status 1","FA status 2","FA status 3","FA status 4","Ancienneté","Année lancement","Durée prévisionnelle","Décalage lancement","Durée lancement","Date ach. initiale","Date ach. Actualisée","Durée réelle","Retard","Indicateur"]
[3003,"Azurfloor, liste des tailles  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34]
[3009,"Dessableur dégraisseur rectangulaire type V , rampes de vibrair  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3031,"Biolite L2.7 cahier des charges  YA.7020  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3033,"Bassins biologiques type chenal de mesure  de vitesse  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3036,"Azurfloor, reprise de plans  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3038,"Pulsator, vérification  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3041,"GDD/GDE, capteur de niveau sortie boues  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3043,"Azurair C, consommation en eau adoucie  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3045,"Vibrair, mise à jour des plans modèle GMB  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3047,"Carbazur Mediazur, buselures  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3049,"Digesteur, détection trop plein  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3053,"Aquazur, qualité du sable  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3057,"Aeroflot en dessablage, changement de gamme  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3058,"Aquazur T , vanne de lavage  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3059,"Biolite P4.5, traduction § 2 et 3.2  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3060,"Azurair C mise à jour  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[3062,"GDD et filtre presse  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4003,"Révision  2005 dossier produit Biofor  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4004,"Révision dossier produit Ultrazur R450  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4005,"Digestion- Gazomètre souple  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4007,"Production dossier produit Flexazur T80S  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4010,"Recommandations pour éviter la présence de mousse autour des réacteurs biologiques  /    /  ",4,"GR Group","Technique",null,null,"Jean Claude BOURDELOT","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4011,"Définition spécification vis de relevage  /    /  ",4,"GR Group","Technique",null,null,"Denis MARCHAND","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[4012,"Mise à jour du dossier produit Régulazur II  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5001,"Corrosion conduites inox dans  environnement chloré  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5009,"Formation sensiblisation aux règles de sécurité  /    /  ",4,"GR Group","Processus",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5010,"Spécification générale affaire  /    /  ",4,"GR Group","Processus",null,null,null,"2006-12-22",null,null,null,34,"",12,null,"","",null,"","",""]
[5012,"précision sur note de calcul HMT pompe  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"",12,null,"","",null,"","",""]
[5015,"Digesteur - trou d'homme  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5016,"Innoplana - Transport de granulé de boues -Sécurité  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5020,"Compresseur, soupape, positionnement  /    /  ",4,"GR Group","Technique",null,null,"Florence GRIMAUD","2007-03-02",null,null,null,34,"","",null,"","",null,"","",""]
[5022," DENSADEG  Mises à jour",3,"GR Group","Technique","DTG","2009-02-18","Jean Louis BRUNET","2007-01-03","2007-02-19","2009-02-18",null,null,"","",null,"","",null,"","",""]
[5023,"Electricité - Connaissances élémentaires  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,2007,18,null,1,"2008-06-26","2009-08-24",31,13,3]
[5025,"Filtre ouvert - GC - Note de calcul  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5026,"Digesteur - GC - Conditions de calcul  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5030,"Plancher monolithique - Cahiers des charges à corriger  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5032,"Supportage , complément dans documentation technique  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5033,"Modification du dossier produit Vibrair  /    /  ",4,"GR Group","Technique","DTG",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5035,"Charbon actif , phase II",3,"GR Group","Technique","PRM","2009-02-18","Jean Louis BRUNET","2007-01-22","2007-02-19","2009-02-18",null,null,"","",null,"","",null,"","",""]
[5040,"Agitateurs - Manutention, maintenance et sécurité  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",null,null,null,34,2007,18,null,0,"2008-07-15","2009-11-30",33,15,3]
[5048,"Filtre FV2B - Parametrage  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5049,"Bassin d'aération - Entrainement d'air dans l'alimentation  /    /  ",4,"GR Group","Technique","DTG",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5050,"Carbonatation par mélange ds eaux du poste toutes eaux  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5052,"Pulsator - Cheminée besoin de couverture  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5055,"Plancher de filtre, dalle de grandes dimensions /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-01-24",null,null,null,34,"","",null,"","",null,"","",""]
[5056,"Planchers monolithiques - Plan standard de ferraillage  /    /  ",4,"GR Group","Technique","PRM - TGC",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5057,"Charbon actif -Phase 1 documentation de conception  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5059,"Atelier de séchage - Température et concentration en poussière des incondensables  /    /  ",4,"GR Group","Technique","DTI",null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]
[5067,"VLE et VME sur NH3, mise à jour documentation  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",null,null,null,34,"","",null,"","",null,"","",""]

{"sheet":"Feuil2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Feuil3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}