{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Export AP_08_10_2009"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Export AP_08_10_2009","index":0,"n_rows":438,"n_cols":16,"rows_kept":438,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Order Nr","Title","Status","Launched by","Topic","Ressources","Status Date","Action Pilot","FA status 1","FA status 2","FA status 3","FA status 4",null,null,"Durée prévisionnelle","Décalage lancement"]
[3003,"Azurfloor, liste des tailles  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22"]
[3009,"Dessableur dégraisseur rectangulaire type V , rampes de vibrair  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3031,"Biolite L2.7 cahier des charges  YA.7020  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3033,"Bassins biologiques type chenal de mesure  de vitesse  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3036,"Azurfloor, reprise de plans  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3038,"Pulsator, vérification  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3041,"GDD/GDE, capteur de niveau sortie boues  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3043,"Azurair C, consommation en eau adoucie  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[3045,"Vibrair, mise à jour des plans modèle GMB  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3047,"Carbazur Mediazur, buselures  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3049,"Digesteur, détection trop plein  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3053,"Aquazur, qualité du sable  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[3057,"Aeroflot en dessablage, changement de gamme  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3058,"Aquazur T , vanne de lavage  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[3059,"Biolite P4.5, traduction § 2 et 3.2  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[3060,"Azurair C mise à jour  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[3062,"GDD et filtre presse  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[4003,"Révision  2005 dossier produit Biofor  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[4004,"Révision dossier produit Ultrazur R450  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[4005,"Digestion- Gazomètre souple  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[4007,"Production dossier produit Flexazur T80S  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[4010,"Recommandations pour éviter la présence de mousse autour des réacteurs biologiques  /    /  ",4,"GR Group","Technique",null,null,"Jean Claude BOURDELOT","2006-12-22",{"$nulls":5},""]
[4011,"Définition spécification vis de relevage  /    /  ",4,"GR Group","Technique",null,null,"Denis MARCHAND","2006-12-22",{"$nulls":5},""]
[4012,"Mise à jour du dossier produit Régulazur II  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[5001,"Corrosion conduites inox dans  environnement chloré  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5009,"Formation sensiblisation aux règles de sécurité  /    /  ",4,"GR Group","Processus",null,null,null,"2006-12-22",{"$nulls":5},""]
[5010,"Spécification générale affaire  /    /  ",4,"GR Group","Processus",null,null,null,"2006-12-22",{"$nulls":5},12]
[5012,"précision sur note de calcul HMT pompe  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},12]
[5015,"Digesteur - trou d'homme  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5016,"Innoplana - Transport de granulé de boues -Sécurité  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5020,"Compresseur, soupape, positionnement  /    /  ",4,"GR Group","Technique",null,null,"Florence GRIMAUD","2007-03-02",{"$nulls":5},""]
[5022," DENSADEG  Mises à jour",4,"GR Group","Technique","DTG","2009-08-24","Jean Louis BRUNET","2007-01-03","2007-02-19","2009-02-18","2009-08-24",null,null,""]
[5023,"Electricité - Connaissances élémentaires  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},18]
[5025,"Filtre ouvert - GC - Note de calcul  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5026,"Digesteur - GC - Conditions de calcul  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5030,"Plancher monolithique - Cahiers des charges à corriger  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5032,"Supportage , complément dans documentation technique  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5033,"Modification du dossier produit Vibrair  /    /  ",4,"GR Group","Technique","DTG",null,null,"2006-12-22",{"$nulls":5},""]
[5035,"Charbon actif , phase II",3,"GR Group","Technique","PRM","2009-02-18","Jean Louis BRUNET","2007-01-22","2007-02-19","2009-02-18",null,null,null,""]
[5040,"Agitateurs - Manutention, maintenance et sécurité  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",{"$nulls":5},18]
[5048,"Filtre FV2B - Parametrage  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[5049,"Bassin d'aération - Entrainement d'air dans l'alimentation  /    /  ",4,"GR Group","Technique","DTG",null,null,"2006-12-22",{"$nulls":5},""]
[5050,"Carbonatation par mélange ds eaux du poste toutes eaux  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5052,"Pulsator - Cheminée besoin de couverture  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",{"$nulls":5},""]
[5055,"Plancher de filtre, dalle de grandes dimensions /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-01-24",{"$nulls":5},""]
[5056,"Planchers monolithiques - Plan standard de ferraillage  /    /  ",4,"GR Group","Technique","PRM - TGC",null,null,"2006-12-22",{"$nulls":5},""]
[5057,"Charbon actif -Phase 1 documentation de conception  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",{"$nulls":5},""]
[5059,"Atelier de séchage - Température et concentration en poussière des incondensables  /    /  ",4,"GR Group","Technique","DTI",null,null,"2006-12-22",{"$nulls":5},""]
[5067,"VLE et VME sur NH3, mise à jour documentation  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5072,"Désodorisation - Analyseur de chlore  /    /  ",4,"GR Group","Technique",null,null,"Patrick DESCAMPS","2006-12-22",{"$nulls":5},""]
[5073,"Filtre - Cahier des charges Anthracite  /    /  ",4,"GR Group","Technique","PRM",null,null,"2006-12-22",{"$nulls":5},""]
[5085,"Boues chaulées - Notion de stockage et de prise en masse  /    /  ",4,"GR Group","Technique","DTI",null,null,"2006-12-22",{"$nulls":5},""]
[5087,"Surpresseurs - local : maintenance  des grilles d' entrée air  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[5088,"Cyclor - accessiblité aux pelles  /    /  ",4,"GR Group","Technique","DTI",null,null,"2006-12-22",{"$nulls":5},""]
[5092,"Automatisme - régulation, besoin de formation  /    /  ",4,"GR Group","Technique","Rueil",null,"Eric GARCIN","2006-12-22",{"$nulls":5},""]
[5094,"Cadre de garantie Eaux Potables  /    /  ",4,"GR Group","Technique",null,null,"Jacques MOLES","2006-12-22",{"$nulls":5},6]
[5095,"Clarificateur SV - Mise  en place des MàJ du KM dans la documentation technique   /    /  ",4,"GR Group","Technique","DTG","2008-05-30","Jean Louis BRUNET","2007-01-22","2007-02-19",null,"2008-05-30",null,null,""]
[5096,"Dessableur-dégraisseur - Biomaster - Remettre les MàJ du KM dans la documentation technique  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},15]
[5097,"Biolite P4.5 - Cahiers des charges y. 7034 et 7000 - Imprécisions  /    /  ",4,"GR Group","Technique","PRM",null,"Denis MARCHAND","2006-12-22",{"$nulls":5},""]
[5098,"Modules lamellaires /    /  ",4,"GR Group","Technique","Rueil",null,"Jean Louis BRUNET","2007-01-24",{"$nulls":5},""]
[5100,"Instrumentation, production de fiches de principe de montage",2,"GR Group","Technique","DEE-DTG","2007-02-19","Patrick DESCAMPS","2006-12-22","2007-02-19",{"$nulls":4},""]
[5109,"Concentrateur à graisses - Mauvais fonctionnement  /    /  ",4,"GR Group","Technique","Rueil","2007-02-15","Jean Louis BRUNET","2006-12-22",{"$nulls":5},18]
[5110,"Cyclor - Pelles CYCLAR - Désamorçage  /    /  ",4,"GR Group","Technique","DTI",null,null,"2006-12-22",{"$nulls":5},""]
[5111,"UF - Plan skid - Réservation mal positionnée  /    /  ",4,"GR Group","Technique","DTI",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[5116,"GC - Réseau de terre",4,"GR Group","Technique",null,"2007-07-20","Charles DE CHAMPEAUX","2006-12-22","2007-02-19","2007-07-20","2007-07-20",null,null,""]
[6006,"Pont - entraînement -  Carénage insuffisant  /    /  ",4,"GR Group","Technique",null,"2007-02-19","Jean Louis BRUNET","2006-12-22","2007-02-19",{"$nulls":4},6]
[6009,"Densadeg - mises à jour",3,"GR Group","Technique","PRM","2009-02-18","Jean Louis BRUNET","2006-12-22","2007-02-19","2009-02-18",null,null,null,""]
[6012,"H2S, impact des sulfures dans les eaux usées",4,"GR Group","Technique","DTG","2008-11-28","Sandrine VENOT","2006-12-22","2007-02-19","2008-11-19","2008-11-28",null,null,18]
[6015,"GMAO (Aquamaint)  documentation  fournisseurs",4,"GR Group","Technique","DTG","2009-02-24","Guy GAUDY","2007-03-02","2007-04-25","2009-02-20","2009-02-24",null,null,12]
[6028,"Azurair C  Note de calcul  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},6]
[6034,"Dessablage  dégraissage- Mesure des performances  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[6040,"Polymère poudre - Fiabilisation préparation  /    /  ",4,"GR Group","Technique",null,null,null,"2006-12-22",{"$nulls":5},""]
[6041,"Plancher - Réutilisation mandrins de buselures  /    /  ",4,"GR Group","Technique",null,null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6047,"Mise à jour Dossier Procédé Biofor  Plus Aéré DHA  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6050,"Plancher monolithique -  dossier construction modification  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6053,"Aquazur , traitement tertaire , perte de sable/    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-01-22",{"$nulls":5},""]
[6064,"UF - Revêtement cuve lessivielle, régulation depuis bache de gavage  /    /  ",4,"GR Group","Technique","Rueil",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6066,"Aquazur V - fiche technique R.303  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-02-05",{"$nulls":5},""]
[6067,"Plancher de filtres , enrobage des fers ,  encoches ,  poutres  et autres /    /  ",4,"GR Group","Technique","TGC - PRM",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6068,"Carbazur - chapitres SKB80A et SKB80B -consignes de sécurité  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-02-05",{"$nulls":5},""]
[6072,"Sédipac 3D , tuyauterie sables , Bouchages ouvrages hors service, écope rotative.",4,"GR Group","Technique","Rueil","2007-01-10","Jean Louis BRUNET","2006-12-22","2007-01-05","2007-01-10","2007-01-10",null,null,""]
[6073,"Densadeg,  fournisseur unique pour l 'agitateur  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-01-22",{"$nulls":5},6]
[6075,"DIGESTEUR  , précisions sur la protection des bétons",4,"GR Group","Technique","PRM - TGC","2007-01-16","Jean Louis BRUNET","2007-01-03",{"$nulls":5},6]
[6076,"Filtre, plancher, épaisseur d'enrobage  /    /  ",4,"GR Group","Technique","TGC - PRM",null,"Jean Louis BRUNET","2007-02-06",{"$nulls":5},""]
[6077,"Buselure 3DS35e, 3DC35e et D21 - Ajout dans normalien N  /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2006-12-22",{"$nulls":5},""]
[6078,"Transfert gravitaire des boues épaissies sous centrifugeuse  /    /  ",4,"GR Group","Technique","DTI",null,"Andre HAUBRY","2006-12-22",{"$nulls":5},""]
[6079,"Biofor, gravier support, qualité /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-02-05",{"$nulls":5},""]
[6080,"GDD , débit massique en fonction de la nature des boues /    /  ",4,"GR Group","Technique","PRM",null,"Jean Louis BRUNET","2007-02-01",{"$nulls":5},""]
[7001,"Pulsator, tuyauterie d'extraction des boues , supportage",4,"GR Group","Technique","PRM","2008-04-02","Jean Louis BRUNET","2007-02-27","2007-04-25",null,"2008-04-02",null,null,""]
[7002,"Prepazur , emplacement du coffret électrique  pour mise en route et intervention ",4,"GR Group","Technique","DTI","2007-10-18","Jean Louis BRUNET","2007-02-27","2007-03-08","2007-10-16","2007-10-18",null,null,6]
[7003,"ARENIS , tambour TD 900  , fissures au niveau des galets ",4,"GR Group","Technique","DTI","2007-10-01","Jean Louis BRUNET","2007-02-27","2007-03-08",null,"2007-10-01",null,null,6]
[7004,"Biofor - divers : accessiblité tamis, sécurité plancher, vibration des déversoirs, perte de biolite , hauteur des lyres ",4,"GR Group","Technique","PRM","2008-04-29","Jean Louis BRUNET","2007-02-27","2007-03-08","2008-04-25","2008-04-29",null,null,6]
[7005,"Biofor aéré - By pass pour mise en route",4,"GR Group","Technique","PRM","2008-04-29","Jean Louis BRUNET","2007-02-27","2007-03-08","2008-04-25","2008-04-29",null,null,12]
[7006,"Biofor - Air de lavage - Caractéristique du silencieux de mise à l'atmosphère de la vanne de décharge ",4,"GR Group","Technique","PRM","2008-04-29","Jean Louis BRUNET","2007-02-27","2007-03-08","2008-04-25","2008-04-29",null,null,6]
[7007,"Biofor - Séquences de lavage - Modification des automatismes ",4,"GR Group","Technique","PRM - DTG","2008-04-29","Jean Louis BRUNET","2007-02-27","2007-03-08","2008-04-25","2008-04-29",null,null,6]
[7008,"Ultrafiltration, caractérisation des eaux ",4,"GR Group","Technique","DTI","2007-05-29","Jean Louis BRUNET","2007-03-01","2007-04-25",null,"2007-05-29",null,null,6]
[7009,"Information sur les travaux en cours chez RDI (DIP) et DTG ",2,"GR Group","Processus","Localite 7009","2008-11-04","Pascal CREANCIER","2007-03-15","2008-11-04",{"$nulls":4},6]
[7010,"Heliantis, poussière , hygiène ",4,"GR Group","Technique","DTI","2007-10-01","Jean Michel FACCIOLI","2007-04-20","2007-04-25","2007-10-01","2007-10-01",null,null,12]
[7011,"Filtres tertiaires note de calcul ",4,"GR Group","Technique","PRM","2007-04-20","Francoise ALEXIADE DUBOIS","2007-04-20","2007-04-20",null,"2007-04-20",null,null,6]
[7012,"Flottation - Petit débit - Pompe d'alimentation du ballon de pressurisation ",4,"GR Group","Technique","PRM","2007-10-18","Jean Louis BRUNET","2007-04-25","2007-04-25","2007-10-15","2007-10-18",null,null,6]
[7013,"Zone anoxique, brassage, positions des agitateurs basse et haute  ",4,"GR Group","Technique","DTG","2007-10-01","Gael CHEVRIER","2007-04-26","2007-04-26",null,"2007-10-01",null,null,6]
[7014,"Gazomètre à membrane, mise en parallèle ",4,"GR Group","Technique","DTG","2009-01-23","Denis MARCHAND","2007-04-26","2007-04-26","2009-01-23","2009-01-23",null,null,6]
[7015,"Acide sulfurique, précicions sur la dilution secondaire ",4,"GR Group","Technique","R&E - DTI","2007-05-09","Francoise ALEXIADE DUBOIS","2007-05-03","2007-05-03",null,"2007-05-09",null,null,6]
[7016,"Anthracites, cahiers des charges Y-7110 et 7120, précisions sur les valeurs de friabilité",4,"GR Group","Technique","PRM - DTI","2007-11-22","Jean Louis BRUNET","2007-05-03","2007-05-03","2007-11-21","2007-11-22",null,null,6]
[7017,"Electricité - Spécification pour les variateurs de fréquence",2,"GR Group","Technique","DTG","2007-05-11","Eric FIEVEZ","2007-05-11","2007-05-11",{"$nulls":4},6]
[7018,"Contrôle commande, réseau de terrain, fiabilité ",4,"GR Group","Technique","DTG","2008-04-02","Jean Pierre HAZARD","2007-05-29","2007-05-29","2008-03-27","2008-04-02",null,null,12]
[7019,"Chaux, dosage, utilité d'un variateur de vitesse",4,"GR Group","Technique","Localite 7019","2007-08-01","Francoise ALEXIADE DUBOIS","2007-06-14","2007-06-14","2007-07-30","2007-08-01",null,null,6]
[7020,"Equilibrage des débits entre filtres sous pression colmatés et non colmatés d?une même batterie",4,"GR Group","Technique","Rueil","2008-02-07","Jean Louis BRUNET","2007-07-19","2007-07-19","2007-12-21","2008-02-07",null,null,6]
[7021,"GDD / GDE compléments",2,"GR Group","Technique","PRM","2007-07-19","Jean Louis BRUNET","2007-07-19","2007-07-19",{"$nulls":4},6]
[7022,"Densadeg , suspension des goulottes de sortie, calcul de la passerelle",2,"GR Group","Technique","PRM","2007-07-19","Jean Louis BRUNET","2007-07-19","2007-07-19",{"$nulls":4},12]
[7023,"Biofor pression plancher ",4,"GR Group","Technique","PRM","2008-04-29","Jean Louis BRUNET","2007-07-19","2007-07-19","2008-04-24","2008-04-29",null,null,18]
[7024,"Veille réglementaire, déchets électriques et électroniques",4,"GR Group","Technique","Rueil siège","2007-08-29","Eric FIEVEZ","2007-08-02","2007-08-02","2007-08-29","2007-08-29",null,null,6]
[7025,"Arénis - muret sous trommel",4,"GR Group","Technique","DTI","2008-02-15","Jean Louis BRUNET","2007-09-04","2007-09-05","2008-02-14","2008-02-15",null,null,6]
[7026,"Dossiers produits BIOFOR, plancher monolithique , support Oxazur",4,"GR Group","Technique","PRM","2007-11-28","Jean Louis BRUNET","2007-09-04","2007-09-04","2007-11-28","2007-11-28",null,null,6]
[7027,"Densadeg, pont, valeur couple entraînement PH2 sur PB erroné",2,"GR Group","Technique","R&E","2007-09-05","Francoise ALEXIADE DUBOIS","2007-09-05","2007-09-05",{"$nulls":4},6]
[7028,"Epaississeur de grand diamètre, intérêt d'un appuis central ",4,"GR Group","Technique","DTG","2007-10-10","Jean Louis BRUNET","2007-10-01","2007-10-01","2007-10-10","2007-10-10",null,null,18]
[7029,"Buselure, procédure de montage, compléments",4,"GR Group","Technique","PRM","2008-01-03","Jean Louis BRUNET","2007-10-18","2007-10-18","2007-12-21","2008-01-03",null,null,6]
[7030,"Ultrazur conception des salles",4,"GR Group","Technique","DTG","2009-06-30","Jean Louis BRUNET","2007-10-18","2007-10-18","2009-06-16","2009-06-30",null,null,6]
[7031,"Ultrazur détente air et eau, double ?",4,"GR Group","Technique","DTG","2009-06-30","Jean Louis BRUNET","2007-10-18","2007-10-18","2009-06-16","2009-06-30",null,null,6]
[7032,"Pressurisation détente compléments",4,"GR Group","Technique","PRM","2008-04-30","Jean Louis BRUNET","2007-11-09","2007-11-09",null,"2008-04-30",null,null,6]
[7033,"Densadeg 4D30,Sédipac D/3D épaississeurs, doc technique ",4,"GR Group","Technique","PRM","2009-08-24","Jean Louis BRUNET","2007-11-13","2007-11-13","2009-08-13","2009-08-24",null,null,6]
[7034,"Têtes d'entraînement -Densadeg, Sédipac et épaississeurs - mise à jour des plans ",4,"GR Group","Technique","PRM-DTG","2007-11-19","Jean Louis BRUNET","2007-11-14","2007-11-14","2007-11-16","2007-11-19",null,null,12]
[7035,"GC, Dalles précontraintes en coffrage et reprise d'effort, procédé à risque  ",4,"GR Group","Technique","TGC - R&E","2008-02-21","Denis MARCHAND","2007-11-27","2007-11-27","2008-02-21","2008-02-21",null,null,12]
[7036,"Digesteur primaire, dossier produit",4,"GR Group","Technique","PRM - DTI - DTG","2009-03-31","Jean Louis BRUNET","2007-11-29","2007-11-29","2009-03-23","2009-03-31",null,null,6]
[7037,"Succir : mise à jour de la standardisation ",2,"GR Group","Technique","DTG - PRM - DEE","2007-11-29","Jean Louis BRUNET","2007-11-29","2007-11-29",{"$nulls":4},12]
[7038,"Racsuc : mise à jour de la standardisation ",2,"GR Group","Technique","DTG - PRM - DEE","2007-11-29","Jean Louis BRUNET","2007-11-29","2007-11-29",{"$nulls":4},18]
[7039,"Flottateur en épaississement de boues : standardisation de l'entraînement central  ",4,"GR Group","Technique","DTG - PRM - DEE","2009-09-29","Jean Louis BRUNET","2007-11-29","2007-11-29","2009-09-22","2009-09-29",null,null,18]
[7040,"Moteur de recherche Doc Tech ",4,"GR Group","Processus","DSI","2008-01-18","Jean Luc NONIN","2008-01-07","2008-01-07",null,"2008-01-18",null,null,18]
[7041,"PREPAZUR - Documentation technique  ",4,"GR Group","Technique","DTI - PRM","2008-01-11","Jean Louis BRUNET","2008-01-07","2008-01-07","2008-01-10","2008-01-11",null,null,12]
[7042,"Refroidissement de l'air surpressé - Note de calcul ",4,"GR Group","Technique","DTI","2009-05-29","Valerie NASTASI","2008-01-28","2008-01-28","2009-04-15","2009-05-29",null,null,6]
[7043,"Aérateur de surface type turbine - Hauteur de revanche des bassins insuffisante ",4,"GR Group","Technique","DTG","2009-07-30","Jean Louis BRUNET","2008-01-28","2008-01-28","2009-06-26","2009-07-30",null,null,12]
[7044,"ECOSKID AQUASOURCE et Offre DGT, validation technique DTG ",4,"GR Group","Technique","Innovation","2008-10-21","Alain MAHEU","2008-01-28","2008-01-28","2008-09-30","2008-10-21",null,null,6]
[7045,"Electricité, Couplage fugitif d'un groupe au réseau sans cellule de protection ",4,"GR Group","Technique","DTG","2008-02-27","Eric FIEVEZ","2008-02-04","2008-02-04","2008-02-18","2008-02-27",null,null,6]
[7046,"Sécurité - Electricité  ",4,"GR Group","Technique","DTG - R&E","2008-07-10","Eric FIEVEZ","2008-02-05","2008-02-05","2008-07-07","2008-07-10",null,null,6]
[7047,"Sécurité alimentation ondulée",4,"GR Group","Technique","DTG","2009-06-30","Regis LANCON","2008-02-06","2008-02-06","2009-06-30","2009-06-30",null,null,6]
[7048,"Télégestion des équipements , WIFI ",4,"GR Group","Technique","DTG","2008-07-30","Guy GAUDY","2008-02-07","2008-02-07","2008-07-30","2008-07-30",null,null,6]
[7049,"Boues activée Injection du chlorure ferrique ",2,"GR Group","Technique","DTI","2008-02-07","Xavier LEBOSSE","2008-02-07","2008-02-07",{"$nulls":4},6]
[7050,"Voiles béton, resistance plein/vide ( fa technique)  ",4,"GR Group","Technique","DTG","2008-02-08","Charles DE CHAMPEAUX","2008-02-08","2008-02-08","2008-02-08","2008-02-08",null,null,12]
[7051,"Base de partage  REX :  trappes intégrant la sécurité :  à sceller lors du coulage du béton ",2,"GR Group","Technique","R&E - SSE","2008-02-11","Francoise ALEXIADE DUBOIS","2008-02-11","2008-02-11",{"$nulls":4},6]
[7052,"Automates : 1 unique standard pour un site donné",4,"GR Group","Technique","DTG","2009-05-28","Jean Pierre HAZARD","2008-02-11","2008-02-11","2009-04-22","2009-05-28",null,null,6]
[7053,"Ultrafor, optimisation de l'offre ",4,"GR Group","Technique","DTI","2009-03-25","Celine PERNOT","2008-02-11","2008-02-11","2008-10-31","2009-03-25",null,null,6]
[7054,"Base de partage REX : Ventilateur plastique - Casse de la volute  - Sécurité ",2,"GR Group","Technique","DTI - R&E","2009-09-09","Michel BURLI","2008-02-13","2008-02-13",{"$nulls":4},6]
[7055,"Base de partage REX : Désodorisation chimique, niveaux des trop-pleins pour les multi-étages, risque de désamorçage des pompes ",2,"GR Group","Technique","DTI","2009-09-09","Michel BURLI","2008-02-13","2008-02-13",{"$nulls":4},6]
[7056,"Désodorisation chimique , prise en compte d'un projet de note technique du Portugal / / ",2,"GR Group","Technique","DTI","2008-02-13","Claude BONEF","2008-02-13","2008-02-13",{"$nulls":4},6]
[7057,"Base ACS et maintenance ACS ",4,"GR Group","Technique","PRM","2009-08-12","Jean Louis BRUNET","2008-02-13","2008-02-13","2009-08-11","2009-08-12",null,null,6]
[7058,"Pompe volumétrique, dévirage et retour en cas d'absence de clapet ",4,"GR Group","Technique","DTG","2009-07-29","Andre HAUBRY","2008-02-20","2008-02-20","2009-07-29","2009-07-29",null,null,12]
[7059,"Réactif , cuve double enveloppe , visualisation des fuites  ",2,"GR Group","Technique","R&E - DEE","2008-02-22","Francoise ALEXIADE DUBOIS","2008-02-22","2008-02-22",{"$nulls":4},6]
[7060,"Pression de refoulement sur réseau de boues déshydratées ",4,"GR Group","Technique","DTI","2009-09-04","Andre HAUBRY","2008-02-22","2008-02-22","2009-08-14","2009-09-04",null,null,12]
[7061,"Epaississement des boues - Mesures et instruments pour bilan masses",4,"GR Group","Technique","DTG","2009-08-14","Patrick DESCAMPS","2008-02-25","2008-02-25","2009-01-26","2009-08-14",null,null,6]
[7062,"Superpress, longueur des toiles ",4,"GR Group","Technique","DTI","2009-07-31","Patrick BELE","2008-02-25","2008-02-25","2009-07-09","2009-07-31",null,null,6]
[7063,"Bache à eau de faible profondeur, agitation  ",4,"GR Group","Technique","DTI","2009-09-14","Andre HAUBRY","2008-02-25","2008-02-25","2009-08-31","2009-09-14",null,null,6]
[7064,"Trémie de dépotage boues chaulées, forme ou traitement des parois  ",4,"GR Group","Technique","DTI","2009-08-26","Andre HAUBRY","2008-02-25","2008-02-25","2009-08-19","2009-08-26",null,null,6]
[7065,"Boues digérées, dégazage et pompes centrifuges ",4,"GR Group","Technique","DTI","2009-09-04","Andre HAUBRY","2008-02-25","2008-02-25","2009-08-14","2009-09-04",null,null,6]
[7066," Déphosphatation biologique et dénitrification, réoxygénation négative des eaux avant introduction à éviter ",2,"GR Group","Technique","DTI","2008-02-25","Philippe GINESTET","2008-02-25","2008-02-25",{"$nulls":4},6]
[7067,"Chaulage boues déshydratées, point d'injection de la chaux ",4,"GR Group","Technique","DTI","2009-08-26","Andre HAUBRY","2008-02-26","2008-02-26","2009-08-19","2009-08-26",null,null,12]
[7068,"Déchargement boues stockées en silo, capacité réelle du grappin  ",4,"GR Group","Technique","DTI","2009-09-04","Andre HAUBRY","2008-02-26","2008-02-26","2009-08-14","2009-09-04",null,null,6]
[7069,"Canalisations d'air vicié, nature et qualité ",2,"GR Group","Technique","DTI","2008-02-26","Valerie NASTASI","2008-02-26","2008-02-26",{"$nulls":4},6]
[7070,"Revues HAZOP et CHAZOP ",2,"GR Group","Technique","R&E - SSE","2008-03-27","Pascal CREANCIER","2008-03-27","2008-03-27",{"$nulls":4},6]
[7071,"Nanofiltration, REX Gaurain Ramecroix ",2,"GR Group","Technique","DTI","2008-09-23","Amandine TINGHIR","2008-03-27","2008-05-19",{"$nulls":4},6]
[7072,"Reverse Osmosis Design - Plant feed back  ",2,"GR Group","Technique","DTI","2008-05-19","Veronique BONNELYE","2008-03-27","2008-05-19",{"$nulls":4},15]
[7073,"Biological Treatment at high temperature ",4,"GR Group","Technique","DTI","2009-01-29","Troy HOLST","2008-03-27","2008-05-19","2008-12-18","2009-01-29",null,null,15]
[7074,"Cyclor Process ",4,"GR Group","Technique","DTI","2009-05-29","Troy HOLST","2008-03-27","2008-05-19","2009-05-29","2009-05-29",null,null,15]
[7075,"Design of Medium/high load activated sludge ",4,"GR Group","Technique","DTI","2009-05-29","Troy HOLST","2008-03-27","2008-05-19","2009-05-29","2009-05-29",null,null,15]
[7076,"Ultrafor, effluent quality and guarantee ",4,"GR Group","Technique","DTI","2009-06-30","Philippe SAVOYE","2008-03-27","2008-05-19","2009-06-30","2009-06-30",null,null,15]
[7077,"High sulfide concentrations, management",4,"GR Group","Technique","DTI","2009-03-16","Troy HOLST","2008-03-27","2008-05-19","2009-02-05","2009-03-16",null,null,15]
[7078,"Gyrazur   Décarbonatation et améliorations",4,"GR Group","Technique","DTI","2009-05-29","Alain MAHEU","2008-03-27","2008-05-19","2009-05-13","2009-05-29",null,null,15]
[7079,"Prétraitement des graisses (avant introduction en Digestion anaérobie) ",4,"GR Group","Technique","DTI","2009-09-18","Andre HAUBRY","2008-03-27","2008-05-19","2009-08-14","2009-09-18",null,null,15]
[7080,"Boues séchées, auto échauffement ",2,"GR Group","Technique","DTI","2008-05-19","Claude PREVOT","2008-03-27","2008-05-19",{"$nulls":4},15]
[7081,"Biogaz et Siloxanes",2,"GR Group","Technique","DTI - DTG","2008-05-19","Claude PREVOT","2008-03-27","2008-05-19",{"$nulls":4},15]
[7082,"Epaississement rapide des boues  ",4,"GR Group","Technique","DTI","2009-08-24","Patrick BELE","2008-03-27","2008-05-19","2009-08-17","2009-08-24",null,null,15]
[7083,"Emissions d'odeurs ",2,"GR Group","Technique","DTI","2008-05-19","Claude BONEF","2008-03-27","2008-05-19",{"$nulls":4},15]
[7084,"Aérateurs mécaniques",2,"GR Group","Technique","DTG","2008-06-11","Olivier BREMOND","2008-03-27","2008-06-11",{"$nulls":4},15]
[7085,"Boues - Deshydratation: non respect des garanties de siccité et surconsommation réactifs ",4,"GR Group","Technique","DXX","2009-07-16","Farah TAHA","2008-03-27","2008-05-19","2009-07-16","2009-07-16",null,null,15]
[7086,"Gestion du Produit Arénis et de son atelier ",2,"GR Group","Technique","DTI - PRM","2008-05-19","Jean Louis BRUNET","2008-03-27","2008-05-19",{"$nulls":4},15]
[7087,"Ondeor, effluent fortement chargé en azote  ",4,"GR Group","Technique","DTI","2008-10-30","Celine PERNOT","2008-03-27","2008-03-27","2008-10-24","2008-10-30",null,null,12]
[7088,"Dossier Produit Methodes SZZ Liquides chargés, mise à jour ",3,"GR Group","Technique","DTI - R&E","2009-09-22","Andre HAUBRY","2008-03-27","2008-03-27","2009-09-22",null,null,null,6]
[7089,"Portail REX, accès direct aux rapports REX  ",2,"GR Group","Processus","R&E","2008-03-27","Isabelle YHUEL","2008-03-27","2008-03-27",{"$nulls":4},6]
[7090,"Polymère - Inertie des longs réseaux ",3,"GR Group","Technique","DTI","2009-08-26","Andre HAUBRY","2008-03-28","2008-03-28","2009-08-26",null,null,null,12]
[7091,"Héliantis, note de calcul ",2,"GR Group","Technique","DTI","2008-03-28","Valerie NASTASI","2008-03-28","2008-03-28",{"$nulls":4},6]
[7092,"Osmose inverse, arrêt pour SDI élevé  ",2,"GR Group","Technique","DTI","2008-07-01","Veronique BONNELYE","2008-03-28","2008-07-01",{"$nulls":4},12]
[7093,"Prépazur, dépôts de sable  ",3,"GR Group","Technique","DTI - PRM","2009-02-13","Jean Louis BRUNET","2008-03-28","2008-05-19","2009-02-13",null,null,null,6]
[7094,"Traitement des graisses, centrifugation avec les boues de Biofor ",4,"GR Group","Technique","DTI","2009-08-24","Andre HAUBRY","2008-03-28","2008-05-19","2009-08-11","2009-08-24",null,null,12]
[7095,"Lingettes  et filasses dans les stations d'ERU ",2,"GR Group","Technique","PRM - DTI - R&E","2008-05-19","Jean Louis BRUNET","2008-03-28","2008-05-19",{"$nulls":4},12]
[7096,"Classe tuyauterie, document unique ",2,"GR Group","Technique","R&E - DEE","2008-12-17","Pascal CREANCIER","2008-04-02","2008-04-02",{"$nulls":4},12]
[7097,"pompe submersible manutention",4,"GR Group","Technique","DEE","2008-10-06","Christophe BALLIGAND","2008-04-23","2008-04-23","2008-08-01","2008-10-06",null,null,6]
[7098,"Héliantis , compléments divers ( accès, bras de scarificateur , coffret elec et poussières)",1,"GR Group","Technique","DTI","2008-04-23",null,"2008-04-23",{"$nulls":5},6]
[7099,"Installation sonde US E+H",4,"GR Group","Technique","DTG","2009-01-26","Patrick DESCAMPS","2008-04-23","2008-04-23","2009-01-26","2009-01-26",null,null,6,18]
[7100,"Densadeg, Sédipac, capteur  voile de boue, réservations",4,"GR Group","Technique","PRM - DTG","2009-09-30","Jean Louis BRUNET","2008-04-29","2008-04-29","2009-08-11","2009-09-30",null,null,6]
[7101,"PULSATOR, PULSATUBE, Tranquillisateurs ",2,"GR Group","Technique","PRM","2008-05-26","Jean Louis BRUNET","2008-05-26","2008-05-26",{"$nulls":4},12]
[7102,"Etudes execution Automatismes",2,"GR Group","Processus","DTG","2008-06-20","Olivier BOULY","2008-05-27","2008-05-27",{"$nulls":4},12]
[7103,"Normes et réglementations locales  ",2,"GR Group","Processus",null,"2008-09-02","Cedric BARET","2008-05-27","2008-05-27","2008-09-02",null,null,null,12]
[7104,"Gestion des modifications / stratégie  ",4,"GR Group","Processus","Omega Processus","2009-09-29","Maryse LITT","2008-05-27","2008-05-27","2009-09-29","2009-09-29",null,null,12]
[7105,"Prise en charge de l'exploitation",2,"GR Group","Processus","Localite 7105","2008-05-27","Damien LECADRE","2008-05-27","2008-05-27",{"$nulls":4},12]
[7106,"Spécification technique d'un équipement pour approbation au Client  ",4,"GR Group","Processus","Omega Processus","2009-06-19","Michel BRETON","2008-05-27","2008-05-27","2008-08-01","2009-06-19",null,null,12]
[7107,"Essais de garanties , nécessité de libellés clairs  ",4,"GR Group","Processus","Omega Processus DPI","2008-09-05","Cedric BARET","2008-05-29","2008-05-29","2008-09-02","2008-09-05",null,null,12]
[7108,"Contrat sous-traitants - des engagements avant signature marché.  ",4,"GR Group","Processus","Omega Processus DPI","2008-09-05","Cedric BARET","2008-05-29","2008-05-29","2008-09-02","2008-09-05",null,null,6]
[7109,"Indiçage des documents contractuels lors de l'élaboration de l'offre  ",2,"GR Group","Processus","Omega Processus DPI","2008-09-02","Cedric BARET","2008-05-29","2008-05-29","2008-09-02",null,null,null,6]
[7110,"  Production d'eau de service  ",2,"GR Group","Technique","DEE - R&E","2008-05-29","Pascal CREANCIER","2008-05-29","2008-05-29",{"$nulls":4},12]
[7111," Clarificateur - Réglage du débit de recirculation des boues biologiques groupe_de travail",4,"GR Group","Technique","R&E - DTI - DTG","2009-08-28","Roger NICOL","2008-05-29","2008-11-04","2009-08-28","2009-08-28",null,null,12]
[7112,"Agitateur - Vibration - Plaque d'assise  ",4,"GR Group","Technique","PRM - DTG","2009-09-30","Jean Louis BRUNET","2008-05-29","2008-11-04","2009-02-13","2009-09-30",null,null,6]
[7113,"Ensembles de dosage - Ergonomie/ accessiblité - Sécurité   Groupe de travail",2,"GR Group","Technique","DEE - R&E","2009-07-02","Christian GAUMARD","2009-06-30","2009-07-02",{"$nulls":4},6]
[7114,"Ultrazur groupe de travail    ",4,"GR Group","Technique","DTI - PRM","2009-06-30","Jean Louis BRUNET","2008-05-29","2008-09-16","2009-06-15","2009-06-30",null,null,6]
[7115,"Couvertures des ouvrages (souples entre autre)    ",1,"GR Group","Technique","DEE","2008-05-29",null,"2008-05-29",{"$nulls":5},6]
[7116,"TUYAUTERIE   DOCUMENTATION TECHNIQUE et FORMATION   Groupe de travail",2,"GR Group","Technique","DEE - R&E","2009-07-02","Christian GAUMARD","2008-05-29","2009-07-02",{"$nulls":4},12]
[7117,"Charbon Actif en Poudre, ATEX   ",1,"GR Group","Technique","R&E - SSE - DTI","2008-05-29",null,"2008-05-29",{"$nulls":5},12]
[7118," Biolite L2.7 Possibilité d'un chargement hydro-pneumatique  ",4,"GR Group","Technique","PRM","2009-06-30","Jean Louis BRUNET","2008-05-29","2008-07-10","2009-04-02","2009-06-30",null,null,6]
[7119,"Clarificateur  / Process Box   /Hauteur périphérique  ",4,"GR Group","Technique","PRM - DTG","2009-09-29","Pascal CREANCIER","2008-05-29","2008-11-04","2009-09-22","2009-09-29",null,null,6]
[7120,"Stockage de réactifs, accessibilité des vannes dans les fosses de rétention  ",4,"GR Group","Technique","R&E","2008-09-05","Gaelle THIEBAUT","2008-05-30","2008-05-30","2008-09-01","2008-09-05",null,null,6]
[7121,"Gérer les quantitatifs E/S et variables  ",2,"GR Group","Processus","Omega Processus","2008-06-20","Olivier BOULY","2008-06-06","2008-06-20",{"$nulls":4},6]
[7122,"Clarificateur, brosses de nettoyage de goulotte de clarificateurs sans électricité, Systeme ROBONET ",4,"GR Group","Technique","DTG","2008-09-05","Jean Jacques NOIRON","2008-06-11","2008-06-11","2008-08-12","2008-09-05",null,null,12]
[7123,"Buselure  4DS25e  ",4,"GR Group","Technique","PRM","2008-07-28","Jean Louis BRUNET","2008-06-18","2008-06-18","2008-07-25","2008-07-28",null,null,6]
[7124,"DB démarrer l'affaire  Spécifier et commander les équipements    ",4,"GR Group","Processus","Omega Processus","2009-09-22","Pascal CREANCIER","2008-06-18","2008-06-18","2009-09-22","2009-09-22",null,null,6]
[7125,"Suivi des modifications  , plans guide",4,"GR Group","Processus","Rueil DEE","2008-07-28","Michel BRETON","2008-06-20","2008-06-20","2008-07-28","2008-07-28",null,null,12]
[7126,"Liste des procédés, installations ou équipements à risque ",4,"GR Group","Processus","Rueil Omega Processus","2009-09-29","Maryse LITT","2008-06-20","2008-06-20","2009-09-29","2009-09-29",null,null,12]
[7127,"Etudes d'execution d'électricité ",4,"GR Group","Processus","Rueil DEE","2008-07-31","Michel BRETON","2008-06-20","2008-06-20","2008-07-31","2008-07-31",null,null,12]
[7128,"Mémoire en réclamation  formation",2,"GR Group","Processus","Rueil Omega processus","2008-06-20","Damien LECADRE","2008-06-20","2008-06-20",{"$nulls":4},12]
[7129,"Etudes de fiabilité de fonctionnement (HAZOP, CHAZOP, AMDE...) fp processus ",4,"GR Group","Processus","Rueil DEE","2009-03-25","Michel BRETON","2008-06-20","2008-06-20","2008-07-29","2008-07-30",null,null,12]
[7130,"PRODUIT NOUVEAU : SUIVI EN EXECUTION (DB Execution) ",4,"GR Group","Processus","Rueil Omega Processus","2009-09-29","Maryse LITT","2008-06-20","2008-06-20","2009-09-29","2009-09-29",null,null,12]
[7131,"Mediazur modifications dans dossier produit et fiches techniques",2,"GR Group","Technique","PRM","2008-09-03","Jean Louis BRUNET","2008-06-23","2008-09-03",{"$nulls":4},12]
[7132,"Concentrateur de graisses (\"Pédalo\") : amélioration et standardisation  ",2,"GR Group","Technique","PRM - DTG","2008-09-03","Jean Louis BRUNET","2008-06-23","2008-09-03",{"$nulls":4},12]
[7133," Bassins d'aération, disposition en \"step feed\", ",2,"GR Group","Technique","DTI","2008-09-03","Troy HOLST","2008-06-23","2008-09-03",{"$nulls":4},12]
[7134,"Désodorisation , tour Javel , régulation inefficace  ",2,"GR Group","Technique","DTI","2008-09-03","Claude BONEF","2008-06-23","2008-09-03",{"$nulls":4},12]
[7135,"Compostage et Odeurs ",2,"GR Group","Technique","DTI","2008-09-03","Claude PREVOT","2008-06-23","2008-09-03",{"$nulls":4},12]
[7136,"Digestion thermophile des boues  ",2,"GR Group","Technique","DTI","2008-09-03","Claude PREVOT","2008-06-23","2008-09-03",{"$nulls":4},15]
[7137,"Pièces contractuelles transmission au service juridique",2,"GR Group","Processus","Localite 7137","2008-06-26","Damien LECADRE","2008-06-26","2008-06-26",{"$nulls":4},15]
[7138,"Site survey ",2,"GR Group","Processus","Localite 7138","2008-06-26","Damien LECADRE","2008-06-26","2008-06-26",{"$nulls":4},15]
[7139,"Explications process à l'Ingénieur Conseil ",3,"GR Group","Processus","Localite 7139","2009-09-29","Maryse LITT","2008-06-26","2008-06-26","2009-09-29",null,null,null,15]
[7140,"Travaux sur Existant - Vade mecum",2,"GR Group","Processus","Omega Processus","2009-08-24","Cedric BARET","2008-06-30","2008-06-30",{"$nulls":4},15]
[7141,"Oméga Ingénierie : Participants aux réunions ",2,"GR Group","Processus","Omega Processus","2008-06-30","Damien LECADRE","2008-06-30","2008-06-30",{"$nulls":4},12]
[7142,"Ingénierie - Réunion Revue de Conception Technique - Participation de l'Expertise  ",4,"GR Group","Processus","Omega Processus","2009-02-17","Michel BRETON","2008-06-30","2008-06-30","2008-07-29","2008-07-30",null,null,12]
[7143,"OMEGA D&B - Modèle de TCO  ",4,"GR Group","Processus","Omega Processus","2009-09-29","Maryse LITT","2008-06-30","2008-06-30","2009-09-29","2009-09-29",null,null,12]
[7144,"D&B - Préparer l'affaire - Valider la vendor list (et pré_choisir les fournisseurs)  ",4,"GR Group","Processus","Omega Processus","2009-09-29","Maryse LITT","2008-06-30","2008-06-30","2009-09-29","2009-09-29",null,null,12]
[7145,"D&B - Modèle de tableau de bord Achats  ",4,"GR Group","Processus","Omega Processus","2009-09-29","Maryse LITT","2008-06-30","2008-06-30","2009-09-29","2009-09-29",null,null,12]
[7146,"\"Produire l'Innovation\" Modification du processus ",4,"GR Group","Processus","Omega Processus","2009-02-09","Armel FONDIN","2008-06-30","2008-06-30","2009-02-05","2009-02-09",null,null,12]
[7147,"Base REX - Impression des fiches de progrès ",4,"GR Group","Processus","R&E","2009-07-06","Isabelle YHUEL","2008-06-30","2008-06-30","2009-07-06","2009-07-06",null,null,12]
[7148,"PLANCHER POLYFLOOR ",4,"GR Group","Technique","PRM","2009-08-14","Jean Louis BRUNET","2008-07-15","2008-09-03","2009-08-11","2009-08-14",null,null,12]
[7149,"Tuyauterie petit diamètre , qualité des isométries  (préparer l'affaire)",4,"GR Group","Processus","DEE Rueil","2009-06-19","Michel BRETON","2008-07-22","2008-07-22","2008-07-29","2009-06-19",null,null,12]
[7150,"Tuyauterie - Vérification ( processus DB)",2,"GR Group","Processus","Rueil Omega processus","2008-07-22","Damien LECADRE","2008-07-22","2008-07-22",{"$nulls":4},12]
[7151,"Planning Consortium ",2,"GR Group","Processus","Rueil Omega processus","2009-06-03","Cedric BARET","2008-07-22","2008-07-22",{"$nulls":4},12]
[7152,"Plancher de filtres, modifications des fiches et plans",4,"GR Group","Technique","PRM","2009-08-25","Jean Louis BRUNET","2008-07-28","2008-07-28","2009-08-12","2009-08-25",null,null,12]
[7153,"Aquazur  Deversoir sortie Eaux  de lavage ",4,"GR Group","Technique","PRM","2009-09-29","Jean Louis BRUNET","2008-07-28","2008-07-28","2009-09-28","2009-09-29",null,null,6]
[7154,"ERI Energy Recovery Device ",2,"GR Group","Technique","DTI","2008-07-29","Frank BOISSEAU","2008-07-28","2008-07-29",{"$nulls":4},12]
[7155,"Filtres FH Bicouche Horizontaux , optimisations  et améliorations",2,"GR Group","Technique","DEE - R&E - PRM","2008-11-04","Pascal CREANCIER","2008-08-01","2008-11-04",{"$nulls":4},15]
[7156,"Prétraitement, ensablement : design des ouvrages d’arrivée",2,"GR Group","Technique","R&E - DTG - DTI","2009-04-23","Christian COITE","2008-08-01","2009-04-23",{"$nulls":4},15]
[7157,"Clarificateur RACSUC de grand diamètre (40m) en eau chaude ",4,"GR Group","Technique","DTG","2008-09-05","Jean Jacques NOIRON","2008-08-01","2008-08-01","2008-08-05","2008-09-05",null,null,6]
[7158,"Classificateur à sable  -et autres retours - circulation en boucle des matières organiques ",2,"GR Group","Technique","DTI","2008-08-01","Troy HOLST","2008-08-01","2008-08-01",{"$nulls":4},6]
[7159,"Dépotage de réactifs - Risque de mauvaise manipulation ",4,"GR Group","Technique","R&E","2009-08-06","Gaelle THIEBAUT","2008-08-11","2008-08-11","2009-08-06","2009-08-06",null,null,6]
[7160,"Création d'une base de spécifications dans Eureka  base_specification",2,"GR Group","Technique","R&E - DEE","2008-08-14","Pascal CREANCIER","2008-08-14","2008-08-14",{"$nulls":4},6]
[7161,"Chaux - Mise à jour documentation Eureka",4,"GR Group","Technique","R&E - DTI","2008-11-27","Gaelle THIEBAUT","2008-08-14","2008-08-14","2008-10-28","2008-11-27",null,null,12]
[7162,"Aquazur V - vannes de sortie des eaux de lavage , type  ",4,"GR Group","Technique","PRM","2009-09-29","Jean Louis BRUNET","2008-08-20","2008-08-20","2009-09-28","2009-09-29",null,null,6]
[7163,"ONDEOR : mise à jour des notes de calcul  ",4,"GR Group","Technique","DTI","2008-10-24","Celine PERNOT","2008-08-22","2008-08-22","2008-10-24","2008-10-24",null,null,6]
[7164,"Chemin de croix standard",2,"GR Group","Processus","Rueil  DB Gagner l'affaire","2008-10-02","Cedric BARET","2008-08-22","2008-10-02",{"$nulls":4},6]
[7165,"Processus DB Gagner l'affaire mise à jour 08 2008",2,"GR Group","Processus","Rueil DB gagenr l'affaire","2008-10-02","Cedric BARET","2008-08-22","2008-10-02",{"$nulls":4},12]
[7166,"Fiche de prix unifiée",2,"GR Group","Processus","Rueil DB gagner l'affaire","2008-08-25","Cedric BARET","2008-08-25","2008-08-25",{"$nulls":4},12]
[7167,"Osmose inverse - Augmentation conductivité dans réservoirs stockage eau osmosée",1,"GR Group","Technique","DTI","2008-08-27",null,"2008-08-27",{"$nulls":5},12]
[7168,"RO - Bache de Lavage tuyauterie d'arrivée  ",4,"GR Group","Technique","R&E - DTI","2009-09-18","Francoise ALEXIADE DUBOIS","2008-08-28","2008-08-28","2009-09-17","2009-09-18",null,null,6]
[7169,"Dewatering /rabattement de nappe, évacuation des eaux  ",4,"GR Group","Technique","TGC","2008-11-12","Charles DE CHAMPEAUX","2008-08-28","2008-08-28","2008-08-29","2008-11-12",null,null,6]
[7170,"CAP en lagune, non décantation ",4,"GR Group","Technique","DTI","2009-07-06","Melanie PAON","2008-08-28","2008-08-28","2009-06-02","2009-07-06",null,null,6]
[7171,"Processus REX, Base REX,  impact qualité à faire apparaitre",4,"GR Group","Processus","R&E","2009-08-26","Pascal CREANCIER","2008-08-29","2008-08-29","2009-08-26","2009-08-26",null,null,6]
[7172,"D&B - Réaliser l'affaire - Liste des fournisseurs / sous-traitants à consulter (Vendor List)",4,"BU Achats et Logistique","Processus","TAA","2008-09-22","Christophe SOULAS","2008-09-08","2008-09-08","2008-09-22","2008-09-22",null,null,12]
[7173,"Thermylis - Mise à jour Dossier Produit",1,"GR Group","Technique","DTG - DTI","2008-09-11",null,"2008-09-11",{"$nulls":5},6]
[7174,"ONDEOR : Hauteur d'eau clarificateurs",4,"GR Group","Technique","DTI","2009-03-31","Celine PERNOT","2008-09-11","2008-09-11","2008-12-18","2009-03-31",null,null,15]
[7175,"Base bruit dans Eureka",2,"GR Group","Technique","R&E","2008-09-11","Pascal CREANCIER","2008-09-11","2008-09-11",{"$nulls":4},12]
[7176,"Emissions odeur et polluants odorants station EVRY  ",2,"GR Group","Technique","DTI","2008-09-11","Claude BONEF","2008-09-11","2008-09-11",{"$nulls":4},15]
[7177,"Dimensionnement d'une cascade d'aération ",4,"GR Group","Technique","DTI - DTG","2008-11-12","Celine PEREZ","2008-09-16","2008-09-16","2008-11-12","2008-11-12",null,null,15]
[7178,"Sécurité - dispositif de consignation ",2,"GR Group","Technique","R&E - SSE","2008-09-17","Mauro LUNA JIMENEZ","2008-09-17","2008-09-17",{"$nulls":4},6]
[7179,"Mise à jour documentation biogaz",4,"GR Group","Technique","PRM","2009-06-30","Jean Louis BRUNET","2008-09-17","2008-11-04","2009-03-24","2009-06-30",null,null,6]
[7180,"Documentation Densadeg Saturateur de Chaux",4,"GR Group","Technique","DTI - PRM","2009-10-05","Gaelle THIEBAUT","2008-09-17","2008-09-17","2009-10-05","2009-10-05",null,null,6]
[7181,"Ancien dossier produit WORD",2,"GR Group","Technique","R&E","2008-09-17","Isabelle YHUEL","2008-09-17","2008-09-17",{"$nulls":4},6]
[7182,"Neutralisation de l'ozone résiduel par le bisulfite",2,"GR Group","Technique","DTI","2008-09-17","Alain MAHEU","2008-09-17","2008-09-17",{"$nulls":4},6]
[7183,"Dégazage : hydraulique et élimination des mousses par raclage des flottants ",2,"GR Group","Technique","DTG","2008-09-18","Jean Jacques NOIRON","2008-09-18","2008-09-18",{"$nulls":4},6]
[7184,"Déchets de prétraitement",2,"GR Group","Technique","DTI - R&E","2008-10-08","Troy HOLST","2008-09-19","2008-10-08",{"$nulls":4},6]
[7185,"Documentation air service",2,"GR Group","Technique","DEE - R&E","2009-07-02","Christian GAUMARD","2008-09-19","2009-07-02",{"$nulls":4},6]
[7186,"Préleveur d'échantillons en charge",4,"GR Group","Technique","DTG","2008-11-17","Francoise ALEXIADE DUBOIS","2008-09-22","2008-09-22","2008-11-13","2008-11-17",null,null,12]
[7187,"Document Eureka : Préparation des réactifs en poudre et Sécurité des opérateurs ",2,"GR Group","Technique","R&E","2008-09-23","Christian GAUMARD","2008-09-23","2008-09-23",{"$nulls":4},6]
[7188,"Tuyauterie en GRP ",2,"GR Group","Technique","DEE","2009-07-02","Christian GAUMARD","2008-09-25","2009-07-02",{"$nulls":4},12]
[7189,"Base REX : Améliorations et chiffrage",4,"GR Group","Processus","R&E","2009-07-06","Isabelle YHUEL","2008-09-26","2008-09-26","2009-06-04","2009-07-06",null,null,12]
[7190,"Processus  DB Gagner l'affaire, spécificité DBO ",2,"GR Group","Processus","Rueil","2008-09-29","Louis ZUCAL","2008-09-29","2008-09-29",{"$nulls":4},12]
[7191,"Processus DB Gagner l'affaire mise à jour 09 2008  ",2,"GR Group","Processus",null,"2008-10-02","Cedric BARET","2008-09-29","2008-10-02",{"$nulls":4},12]
[7192,"Environnements corrosifs et classification : appellation coefficients C1 et C2",4,"GR Group","Technique","R&E","2009-08-12","Francoise ALEXIADE DUBOIS","2008-09-30","2008-09-30","2009-08-11","2009-08-12",null,null,12]
[7193,"Diffusion de chaleur autour d'un tuyau d'air surpressé enterré  ",4,"GR Group","Technique","R&E - DTG","2009-04-10","Gaelle THIEBAUT","2008-09-30","2009-04-07","2009-04-09","2009-04-10",null,null,6]
[7194,"Eureka : Réservoirs métalliques et Corrosion des tôles de fond ",2,"GR Group","Technique","R&E","2008-11-21","Isabelle YHUEL","2008-09-30","2008-11-21",{"$nulls":4},6]
[7195,"NDC bâche de pompage",4,"GR Group","Technique","NDC","2009-04-21","Gregory GNOS","2008-09-30","2008-11-21","2008-12-17","2009-04-21",null,null,6]
[7196,"Processus REX clarification et amélioration ",4,"GR Group","Processus","R&E","2008-11-12","Pascal CREANCIER","2008-09-30","2008-09-30","2008-10-13","2008-11-12",null,null,6]
[7197,"Specifications Techniques Azurair C  ",1,"GR Group","Technique","DTI","2008-09-30","Isabelle YHUEL","2008-09-30",{"$nulls":5},12]
[7198,"Complément Eureka : Spiral flow et inversion du courant",4,"GR Group","Technique","DTG","2009-09-30","Olivier BREMOND","2008-10-06","2008-10-06","2009-09-29","2009-09-30",null,null,6]
[7199,"Transport et Traitement des déchets (ingenierie)  ",4,"GR Group","Processus","Rueil DEE","2009-03-25","Michel BRETON","2008-10-08","2008-10-08","2008-10-08","2009-03-25",null,null,6]
[7200,"D&B - Maîtriser la sous-traitance ingénierie ",2,"GR Group","Processus","Rueil DEE","2008-10-08","Eric GARCIN","2008-10-08","2008-10-08",{"$nulls":4},12]
[7201,"D&B - Finaliser la conception générale - Réunion de conception technique ",4,"GR Group","Processus","Rueil DEE","2009-03-25","Michel BRETON","2008-10-08","2008-10-08","2009-03-25","2009-03-25",null,null,12]
[7202,"Instrumentation en protocole HART ",2,"GR Group","Processus","ING","2008-10-08","Olivier BOULY","2008-10-08","2008-10-08",{"$nulls":4},12]
[7203,"CERTIFICAT ORIGINE EU  ",4,"GR Group","Processus","RUEIL Achat logistique","2008-11-04","Dominique MAGNET","2008-10-08","2008-10-08","2008-10-20","2008-11-04",null,null,12]
[7204,"Plans Guides GC , mise à jour check-list",4,"GR Group","Technique","R&E","2009-09-22","Pascal CREANCIER","2008-10-09","2008-10-09","2009-09-14","2009-09-22",null,null,12]
[7205,"FICHE ACTION   7205",1,"BU China","Technique","Localite 7205","2008-10-14",null,"2008-10-14",{"$nulls":5},6]
[7206,"Building permit / permis de construire",2,"GR Group","Processus","DPI","2008-10-28","Cedric BARET","2008-10-28","2008-10-28",{"$nulls":4},""]
[7207,"Mesure de dureté en continu  ",4,"GR Group","Technique","DTG","2009-06-17","Patrick DESCAMPS","2008-10-29","2008-10-29","2009-01-26","2009-06-17",null,null,12]
[7208,"Chemicals, KMnO4 (potassium permanganate solution) damage of stator and mechanical seals of Progress Cavity Pumps  ",3,"GR Group","Technique","DTI","2009-06-16","Alain MAHEU","2008-10-29","2008-10-29","2009-06-16",null,null,null,6]
[7209,"Omega Numbering System ",4,"GR Group","Processus","Rueil DEE","2009-04-27","Michel BRETON","2008-10-30","2008-10-30","2008-11-03","2009-04-27",null,null,6]
[7210,"DENSADEG GOULOTTES DE REPRISES D'EAU CLARIFIEE  ",4,"GR Group","Technique","PRM - DTI","2009-01-27","Jean Jacques NOIRON","2008-10-30","2008-10-30","2009-01-07","2009-01-27",null,null,12]
[7211,"Analyseur de Fouling index (SDI)  ",4,"GR Group","Technique","TAA","2009-09-21","Thierry MICHEL","2008-10-31","2008-11-07","2009-09-16","2009-09-21",null,null,6]
[7212,"Base de partage REX : Tuyauterie en GRP, dégradation par les UV / GRP PIPE DAMAGED BY AQUARAY H20 REACTOR UV LIGHT  ",2,"GR Group","Technique","R&E","2008-10-31","Michel BURLI","2008-10-31",{"$nulls":5},6]
[7213,"Décanteurs primaires ou secondaires : quelle concentration de boues ?  ",2,"GR Group","Technique","DTI","2008-11-21","Patrick VION","2008-10-31","2008-11-21",{"$nulls":4},6]
[7214,"Droits de signature sur les contrats de Co-Traitance et Sous-traitance ",3,"GR Group","Processus","Omega Processus","2009-09-29","Maryse LITT","2008-11-18","2008-11-18","2009-09-29",null,null,null,6]
[7215,"Standard Contract for Transportation/Contrat de sous-traitance pour le transport",2,"GR Group","Processus","Achats","2008-11-18","Marie Claude NUMA","2008-11-18","2008-11-18",{"$nulls":4},12]
[7216,"Gérer les achats et la logistique - Mise à jour majeure",4,"GR Group","Processus","Achats","2009-09-22","Maxime LE GOFF","2008-11-18","2008-11-18","2009-09-22","2009-09-22",null,null,12]
[7217,"Aérateur INVENT - mise en oeuvre  ",2,"GR Group","Technique","R&E - DTG","2008-11-21","Pascal CREANCIER","2008-11-21","2008-11-21",{"$nulls":4},12]
[7218,"EUREKA : OPTIMISATION DU POMPAGE DU LAIT DE CHAUX PAR POMPE A LOBES ",4,"GR Group","Technique","DTI","2008-11-27","Gaelle THIEBAUT","2008-11-25","2008-11-25","2008-11-26","2008-11-27",null,null,6]
[7219,"Base pour check-list depuis le portail REX",2,"GR Group","Processus","R&E","2008-11-25","Isabelle YHUEL","2008-11-25","2008-11-25",{"$nulls":4},12]
[7220,"Gérer les Produits - Renouvellement ACS",1,"GR Group","Processus","PRM","2008-11-25",null,"2008-11-25",{"$nulls":5},12]
[7221,"Arrêté assainissement 22/06/2007 (abroge l'arrêté du 22/12/1994)",4,"GR Group","Technique","R&E","2009-09-04","Gaelle THIEBAUT","2008-11-25","2009-07-08","2009-09-03","2009-09-04",null,null,12]
[7222,"Dilution et mélange de réactifs",2,"GR Group","Technique","DEE - DTI - R&E","2009-07-02","Christian GAUMARD","2008-11-27","2009-07-02",{"$nulls":4},6]
[7223,"AP Note de calcul ONDEOR  ",2,"GR Group","Technique","DTI","2008-11-28","Celine PERNOT","2008-11-28","2008-11-28",{"$nulls":4},6]
[7224,"AP \"Azurair C - Qualité d'eau d'appoint \"",2,"GR Group","Technique","DTI","2008-11-28","Claude BONEF","2008-11-28","2008-11-28",{"$nulls":4},6]
[7225,"AP \"Tours de désodorisation chimique, Dévésiculeurs\"  ",2,"GR Group","Technique","DTI","2008-11-28","Claude BONEF","2008-11-28","2008-11-28",{"$nulls":4},6]
[7226,"Clapet sur anneau de lubrification refoulement boues deshydratées  ",2,"GR Group","Technique","DTI","2008-12-04","Isabelle YHUEL","2008-12-04","2008-12-04",{"$nulls":4},6]
[7227,"POMPAGE DES BOUES PAR DES POMPES A LOBES, OPTIMISATION ",4,"GR Group","Technique","DTI - R&E","2009-10-05","Isabelle YHUEL","2008-12-04","2008-12-04","2009-10-05","2009-10-05",null,null,6]
[7228,"Processus REX, un autre indicateur : les origines des fiches progrès par affaire ou type d'affaire  ",3,"GR Group","Processus","R&E","2009-06-30","Pascal CREANCIER","2008-12-10","2008-12-10","2009-06-30",null,null,null,6]
[7229,"Processus REX, un autre indicateur pour vérifier son efficacité : nombre de fp par produit, voire domaine ou processus  ",4,"GR Group","Processus","R&E","2009-07-29","Michel BURLI","2008-12-10","2008-12-10",null,"2009-07-29",null,null,12]
[7230,"COMMANDES et Termes Paiement : ASSISTANCE FOURNISSEUR EN OPTION",2,"GR Group","Processus","TAA","2009-09-22","Maxime LE GOFF","2008-12-11","2009-09-22",{"$nulls":4},12]
[7231,"Gérer les Achats et la logistique - KAPPA",2,"GR Group","Processus","TAA","2008-12-11","Maxime LE GOFF","2008-12-11","2008-12-11",{"$nulls":4},12]
[7232,"Mise à jour Processus Achats - Achats hors production",4,"GR Group","Processus","TAA","2008-12-12","Maxime LE GOFF","2008-12-11","2008-12-11","2008-12-12","2008-12-12",null,null,12]
[7233,"Mise à jour Processus DB - Divers achats",4,"GR Group","Processus","Omega DB","2009-09-29","Maryse LITT","2008-12-12","2009-07-06","2009-09-29","2009-09-29",null,null,12]
[7234,"Mise à jour Processus DB - Spécifier et Commander ",4,"GR Group","Processus","TAA - Omega DB","2009-09-29","Maryse LITT","2008-12-12","2009-07-06","2009-09-29","2009-09-29",null,null,12]
[7235,"Gestion des matériels livrés sur chantier",4,"GR Group","Processus","TAA","2009-09-29","Maxime LE GOFF","2008-12-12","2008-12-12","2009-09-22","2009-09-29",null,null,12]
[7236,"Processus DB - Stratégie d'affaire",1,"GR Group","Processus","Omega DB","2008-12-12",null,"2008-12-12",{"$nulls":5},12]
[7237,"Processus DB - Certification CE",1,"GR Group","Processus","Omega DB","2008-12-12",null,"2008-12-12",{"$nulls":5},12]
[7238,"Mise à jour Processus Achat - Gérer les achats et la logistique",2,"GR Group","Processus","TAA","2008-12-12","Maxime LE GOFF","2008-12-12","2008-12-12",{"$nulls":4},12]
[7239,"Processus Achats -> Périmètre d'application du sous processus ACHATS HORS PRODUCTION",2,"GR Group","Processus","TAA","2009-09-22","Maxime LE GOFF","2008-12-12","2008-12-12",{"$nulls":4},12]
[7240,"D&B-Gagner l'affaire-Etablir des conventions signées avec les fournisseurs d'équipements stratégiques",2,"GR Group","Processus","TAA","2009-09-22","Michel BOUCHER","2008-12-12","2009-09-22",{"$nulls":4},12]
[7241,"Mélange - choix de la technologie d'agitation et du fournisseur",4,"GR Group","Technique","DTI","2009-09-30","Olivier BREMOND","2008-12-12","2008-12-12","2009-09-29","2009-09-30",null,null,12]
[7242,"Eureka : Conditions de fonctionnements et d'installation d'un ballon anti-bélier ARAA  ",2,"GR Group","Technique","R&E - DTG","2008-12-16","Isabelle YHUEL","2008-12-16","2008-12-16",{"$nulls":4},6]
[7243,"Vannes de contrôle : choix techniques et fournisseurs",2,"GR Group","Technique","DTG","2008-12-16","Christian COITE","2008-12-16","2008-12-16",{"$nulls":4},6]
[7244,"Ergonomie",1,"GR Group","Processus","Groupe de travail","2008-12-16",null,"2008-12-16",{"$nulls":5},6]
[7245,"Vibrair Mise à jour Documentation Dossier Produit ",4,"GR Group","Technique","DTG","2009-03-31","Jean Louis BRUNET","2008-12-17","2008-12-17","2009-03-25","2009-03-31",null,null,12]
[7246,"Problèmes de corrosion",1,"GR Group","Technique","R&E","2008-12-18",null,"2008-12-18",{"$nulls":5},6]
[7247,"Mise à jour Processus Innovation ",2,"GR Group","Processus","REX & Processus","2008-12-18","Armel FONDIN","2008-12-18","2008-12-18",{"$nulls":4},6]
[7248,"Mise à jour Processus DB - Terminer l'affaire",1,"GR Group","Processus","Omega Processus","2008-12-18",null,"2008-12-18",{"$nulls":5},12]
[7249,"Processus Staffer",2,"GR Group","Processus",null,"2008-12-18","Olivier LEVIEILS","2008-12-18","2008-12-18",{"$nulls":4},12]
[7250,"Densadeg métalliques - Joints hydrogonflants  ",4,"GR Group","Technique","DTG","2009-05-20","Jean Louis BRUNET","2008-12-19","2008-12-19","2009-05-13","2009-05-20",null,null,12]
[7251,"Filtres et biofiltres : représentation des efforts sur les plans guides GC ",2,"GR Group","Technique","PRM","2008-12-19","Jean Louis BRUNET","2008-12-19","2008-12-19",{"$nulls":4},6]
[7252,"Personnel de chantier étranger - Gestion RH",2,"GR Group","Processus","RH","2008-12-19","Olivier LEVIEILS","2008-12-19","2008-12-19",{"$nulls":4},6]
[7253,"Sécurité - Alarme dans locaux à risques lors de coupures de courant",1,"GR Group","Technique","DTG - SSE","2008-12-22",null,"2008-12-22",{"$nulls":5},12]
[7254,"Sécurité - Outillage antidéflagrant pour équipement antidéflagrant 5090",2,"GR Group","Technique","DEE - DTG - SSE","2008-12-22","Mauro LUNA JIMENEZ","2008-12-22","2008-12-22",{"$nulls":4},6]
[7255,"Automatisme des modes de marche BIOFORS ",4,"GR Group","Technique","PRM - DEE","2009-04-30","Jean Louis BRUNET","2008-12-22","2008-12-22","2009-03-23","2009-04-30",null,null,6]
[7256,"Optimisation Travaux Génie Civil - Coût d'excavation ",2,"GR Group","Processus",null,"2008-12-22","Cedric BARET","2008-12-22","2008-12-22",{"$nulls":4},6]
[7257,"DOCTEC : MADIC, liste de référence ",1,"GR Group","Processus",null,"2008-12-22",null,"2008-12-22",{"$nulls":5},12]
[7258,"Automatisme - Documents manquants & difficultés de mise en route en découlant ",2,"GR Group","Processus","DTG","2008-12-23","Armel FONDIN","2008-12-23","2008-12-23",{"$nulls":4},12]
[7259,"Processus \"gagner l'affaire\", aspects juridiques  JV Agreement",2,"GR Group","Processus","Rueil ","2009-01-20","Cedric BARET","2009-01-20","2009-01-20",{"$nulls":4},12]
[7260," Déphosphatation physico-chimique - Calage des courbes de consommation de réactifs  ",1,"GR Group","Technique","DTI","2009-01-29",null,"2009-01-29",{"$nulls":5},12]
[7261,"Déphosphatation tertiaire poussée, ANALYSEUR en CONTINU de P tot & P PO4 pour ajustement de l'injection en FECL3 ",1,"GR Group","Technique","DTI","2009-01-29",null,"2009-01-29",{"$nulls":5},15,8]
[7262,"Courroies d'entraînement et économies d'énergie ",2,"GR Group","Technique","DTG (DES)","2009-09-14","Eric FIEVEZ","2009-01-29","2009-09-14",{"$nulls":4},12,8]
[7263,"Thermylis Note de calcul  ",4,"GR Group","Technique","DTI","2009-09-29","Magalie DENISAN","2009-01-29","2009-02-23","2009-09-28","2009-09-29",null,null,12]
[7264,"Barcelona plant : start-up and 1st year of operation  ",2,"GR Group","Technique","DTI","2009-03-24","Sarah LE GALLOU","2009-01-29","2009-03-24",{"$nulls":4},12]
[7265,"Commande exécutoire - Transmission des documents ",2,"GR Group","Processus","DPI","2009-01-29","Patrick THEROND","2009-01-29","2009-01-29",{"$nulls":4},15]
[7266,"Procédures Codis (DSA ,DsaS, Espagne)  / Oméga \"gagner l'affaire\" homogébisation",2,"GR Group","Processus","DPI ","2009-01-29","Cedric BARET","2009-01-29","2009-01-29",{"$nulls":4},12]
[7267,"Reprise des flottants sur les clarificateurs PB 005 ",4,"GR Group","Technique","R&E ","2009-09-22","Pascal CREANCIER","2009-02-11","2009-02-11","2009-09-22","2009-09-22",null,null,12]
[7268,"Documentation : Réduction des espaces confinés en tout genre  ",2,"GR Group","Technique","R&E - SSE - DEE","2009-02-20","Mauro LUNA JIMENEZ","2009-02-20","2009-02-20",{"$nulls":4},6]
[7269,"Eureka: Settlement of Silt /Sand in Pre-Settler  ",4,"GR Group","Technique","DTI","2009-04-30","Bernard HINAUT","2009-02-23","2009-02-23","2009-03-26","2009-04-30",null,null,6]
[7270,"Filtres et biofiltres béton : trou d'homme ",4,"GR Group","Technique","PRM - SSE - DEE","2009-04-30","Jean Louis BRUNET","2009-02-23","2009-02-23","2009-03-31","2009-04-30",null,null,6]
[7271,"DIMENSIONNEMENT DU DEGAZAGE  avant clarification  ERU",2,"GR Group","Technique","DTG","2009-08-14","Olivier BREMOND","2009-02-23","2009-08-14",{"$nulls":4},6]
[7272,"MIEUX QUALIFIER LES GARANTIES D'UNITE D'ODEUR",4,"GR Group","Technique","DTI","2009-03-16","Celine PEREZ","2009-02-24","2009-02-25","2009-03-16","2009-03-16",null,null,6]
[7273,"Brassage des bassins tampons",1,"GR Group","Technique","DTG","2009-02-24",null,"2009-02-24",{"$nulls":5},6]
[7274,"sujets Poséidon Planet ",1,"GR Group","Technique",null,"2009-02-25",null,"2009-02-25",{"$nulls":5},6]
[7275,"Ultrafor   groupe de travail",4,"GR Group","Technique","R&E - DTI","2009-06-30","Philippe SAVOYE","2009-02-27","2009-02-27","2009-06-26","2009-06-30",null,null,6]
[7276,"Zonas \"non aedificandi\"",2,"BU Portugal","Technique","Localite 7276","2009-03-12","Vitor LOPES","2009-03-12","2009-03-12",{"$nulls":4},6]
[7277,"Silo de stockage de boues séchées sondes de température  ",2,"GR Group","Technique","DTI","2009-03-16","Claude PREVOT","2009-03-16","2009-03-16",{"$nulls":4},""]
[7278,"SECHAGE/COLONNE CONDENSATION: ODEURS des CONDENSATS et CARBONATATION",4,"GR Group","Technique","DTI","2009-09-14","Andre HAUBRY","2009-03-16","2009-03-16","2009-08-14","2009-09-14",null,null,6]
[7279,"DIGECO, mise à jour des fiches techniques ",2,"GR Group","Technique","DTI - PRM","2009-03-23","Claude PREVOT","2009-03-23","2009-03-23",{"$nulls":4},6]
[7280,"FLOWMETER ACCURACY – SUPPLIER SELECTION ",4,"GR Group","Technique","DTG","2009-09-30","Patrick DESCAMPS","2009-03-26","2009-03-27","2009-09-30","2009-09-30",null,null,6]
[7281,"Instrumentation : Mise en dérivation des analyseurs d'eau",2,"GR Group","Technique","DTG","2009-03-27","Patrick DESCAMPS","2009-03-27","2009-03-27",{"$nulls":4},6]
[7282,"MAGNETIC FLOWMETER FOR CHEMICAL DOSING LINES ",4,"GR Group","Technique","DTG","2009-09-30","Patrick DESCAMPS","2009-03-31","2009-03-31","2009-09-30","2009-09-30",null,null,6]
[7283,"Base REX support des sujets Santé Sécurité et Environnement ",2,"GR Group","Processus","R&E","2009-04-02","Michel BURLI","2009-04-02","2009-04-02",{"$nulls":4},6]
[7284,"Participation des coordinateurs Santé Sécurité et des coordinateurs Environnement aux comités REX  ",2,"GR Group","Processus","SSE","2009-04-02","Jean Marc TAYON","2009-04-02","2009-04-02",{"$nulls":4},12]
[7285,"Densadeg 2D 100 : mesure de niveau du voile de boue",1,"GR Group","Technique","DTG - DTI","2009-04-23","Patrick DESCAMPS","2009-04-23",{"$nulls":5},12]
[7286,"Dossier Produit Biofor : chapitre Automatismes à compléter ",1,"GR Group","Technique","DTG","2009-04-23",null,"2009-04-23",{"$nulls":5},12]
[7287,"O&M desalination problematics : Fujairah I plant application ",1,"GR Group","Technique","DTI","2009-04-23",null,"2009-04-23",{"$nulls":5},12,6]
[7288,"Emplacement de l'instrumentation en chloration ",1,"GR Group","Technique","DTG - R&E","2009-04-28",null,"2009-04-28",{"$nulls":5},15,6]
[7289,"Vannes de coupure en chloration / Fiabilité en cas de coupure énergétique",2,"GR Group","Technique","SSE - R&E - DEE","2009-04-28","Mauro LUNA JIMENEZ","2009-04-28","2009-04-28",{"$nulls":4},6]
[7290,"Aquadaf Pneumatic outlet weir ",2,"GR Group","Technique","DTI - PRM","2009-04-29","Patrick VION","2009-04-29","2009-04-29",{"$nulls":4},6]
[7291,"Filtres EP : reprise des chapitres Automatisme",2,"GR Group","Technique","DTG","2009-04-29","Marie SECONDAT","2009-04-29","2009-04-29",{"$nulls":4},6]
[7292,"Filtres et biofiltres béton : accès sous plancher ",1,"GR Group","Technique","PRM - SSE","2009-05-07",null,"2009-05-07",{"$nulls":5},8]
[7293,"Densadeg  modification mineure DP",2,"GR Group","Technique","DTI - PRM","2009-08-25","Jean Louis BRUNET","2009-05-29","2009-08-25",{"$nulls":4},12]
[7294,"GERER LES ACHATS ET LA LOGISTIQUE : RECOMMANDATIONS GOOD CORPORATION",4,"GR Group","Processus","TAA","2009-09-22","Christophe SOULAS","2009-05-29","2009-05-29","2009-09-22","2009-09-22",null,null,6]
[7295,"Prétraitement, quantité et qualité des refus, analyse des évolutions ",2,"GR Group","Technique","R&E - DTI","2009-06-30","Michel BURLI","2009-06-30","2009-06-30",{"$nulls":4},12]
[7296,"Base de partage REX  :Ventilateurs pour désodorisation placés APRES les tours  ",2,"GR Group","Technique","R&E","2009-06-30","Pascal CREANCIER","2009-06-30","2009-06-30",{"$nulls":4},6]
[7297,"Base Outils et check list  REX : Gestion documentaire après commande ",1,"GR Group","Processus","R&E","2009-06-30",null,"2009-06-30",{"$nulls":5},3]
[7298,"Base de partage REX  : POMPES H.P.(en osmose inverse) CONDITIONS D'ALIMENTATION  HYDRAULIQUES",1,"GR Group","Technique","R&E","2009-06-30",null,"2009-06-30",{"$nulls":5},12]
[7299,"Base de partage REX  : Cannon Mixer : Instrumentation et condition climatique ",1,"GR Group","Technique","R&E ","2009-06-30",null,"2009-06-30",{"$nulls":5},3]
[7300,"Base de partage REX  : Cannon Mixer: Equipotentialité des réseaux ",1,"GR Group","Technique","R&E","2009-06-30",null,"2009-06-30",{"$nulls":5},3]
[7301,"Base de partage REX  : ULTRAZUR : retrolavage, qualité de l'eau de dilution ",1,"GR Group","Technique","R&E","2009-06-30",null,"2009-06-30",{"$nulls":5},3]
[7302,"TAMISAGE DEVANT ULTRAFOR ",2,"GR Group","Technique","DTI","2009-07-31","Mathieu GAILLARD","2009-06-30","2009-07-31",{"$nulls":4},3]
[7303,"PLANNING TYPE - DEMARRER L'AFFAIRE",1,"GR Group","Processus","Processus Ingenierie","2009-06-30",null,"2009-06-30",{"$nulls":5},15]
[7304,"Dossier Produit GYRAZUR",2,"GR Group","Technique","DTI","2009-07-03","Francois LE QUESNE","2009-07-03","2009-07-03",{"$nulls":4},12]
[7305,"Turbocirculator en clarification EP ",1,"GR Group","Technique","PRM","2009-07-03",null,"2009-07-03",{"$nulls":5},15]
[7306,"Abattement du manganèse ",1,"GR Group","Technique","DTI","2009-07-03",null,"2009-07-03",{"$nulls":5},12,3]
[7307,"Analyse des paramètres majeurs dans les boues ",2,"GR Group","Technique","DTI","2009-08-05","Claude PREVOT","2009-07-03","2009-08-05",{"$nulls":4},15,3]
[7308,"archives of technical documents ",2,"GR Group","Processus","DEE","2009-07-07","Michel BRETON","2009-07-07","2009-07-07",{"$nulls":4},15]
[7309,"Listes des fiches de progès sous xls // Progress documents list exported to EXCEL  ",2,"GR Group","Processus","R&E","2009-07-07","Isabelle YHUEL","2009-07-07","2009-07-07",{"$nulls":4},12]
[7310,"DENSADEG 2D100 A ALIMENTATION DOUBLE : ENTRAINEMENT D'AIR DANS LE COAGULATEUR  ",2,"GR Group","Technique","DTI - PRM","2009-07-08","Jean Louis BRUNET","2009-07-08","2009-07-08",{"$nulls":4},12]
[7311,"DENSADEG : Doctrines Densadeg(s), annotations ",4,"GR Group","Technique","PRM - DTI","2009-09-08","Jean Louis BRUNET","2009-07-08","2009-07-08","2009-08-21","2009-09-08",null,null,6]
[7312,"Amélioration des réunions de risques et opportunités ",2,"GR Group","Processus",null,"2009-07-09","Cedric BARET","2009-07-09","2009-07-09",{"$nulls":4},6]
[7313,"ULTRAFOR : Manchettes de raccordement  des cassettes ZW500D ",2,"GR Group","Technique","DTI","2009-07-09","Jean Pierre ROUX","2009-07-09","2009-07-09",{"$nulls":4},12]
[7314,"Validation de la conception hydraulique des projets  ",1,"GR Group","Processus",null,"2009-07-09",null,"2009-07-09",{"$nulls":5},6]
[7315,"Boues d'ERU - déshydratation - mise à jour des doctrines ",3,"GR Group","Technique","DTI","2009-09-30","Andre HAUBRY","2009-07-30","2009-07-30","2009-09-30",null,null,null,12]
[7316,"Ultrafor : Soft et Documents d'exploitation client  ",2,"GR Group","Technique","DTI - DTG","2009-07-31","Philippe SAVOYE","2009-07-31","2009-07-31",{"$nulls":4},6]
[7318,"ULTRAFOR - Revêtements des bétons de  la bâche d'eaux sales",2,"GR Group","Technique","DTI","2009-07-31","Philippe SAVOYE","2009-07-31","2009-07-31",{"$nulls":4},6]
[7319,"INCENDIE CUVE DE STOCKAGE SOUDE - SONDE CHAUFFANTE",4,"GR Group","Technique","R&E","2009-09-10","Celine PEREZ","2009-08-10","2009-08-10","2009-09-10","2009-09-10",null,null,6]
[7320,"Procédures et revues de vérification/Validation ",2,"GR Group","Processus",null,"2009-09-18","Thibaud GENTON","2009-08-24","2009-09-18",{"$nulls":4},6]
[7321,"Prestations Internes: Liste et qualité des livrables  ",1,"GR Group","Processus",null,"2009-08-24",null,"2009-08-24",{"$nulls":5},12]
[7322,"Réunions \"War Room\" prise de décision choix des équipements ",1,"GR Group","Processus",null,"2009-08-25",null,"2009-08-25",{"$nulls":5},12]
[7323,"Processus de passation de marchés de travaux en phase affaire , Questionnaire agreement  ",2,"GR Group","Processus",null,"2009-08-25","Patrick THEROND","2009-08-25","2009-08-25",{"$nulls":4},12]
[7324," Fixation sur parois béton  ",2,"GR Group","Technique","R&E","2009-08-27","Gaelle THIEBAUT","2009-08-27","2009-08-27",{"$nulls":4},12]
[7325,"Processus Gagner l'affaire. cohérence globale de l'offre (prix, plan, offre) ",2,"GR Group","Processus",null,"2009-08-27","Cedric BARET","2009-08-27","2009-08-27",{"$nulls":4},6]
[7326,"Tuyauteries petits diamètres, qualité des isométries (Gagner l'affaire)  ",2,"GR Group","Processus",null,"2009-08-27","Michel BRETON","2009-08-27","2009-08-27",{"$nulls":4},12]
[7327,"VIBRAIR - modification du dossier produit ",2,"GR Group","Technique","DTG - PRM","2009-08-27","Jean Louis BRUNET","2009-08-27","2009-08-27",{"$nulls":4},12]
[7328,"lavage filtre , automatisme, groupe de travail",1,"GR Group","Technique","PRM - DTI - DEE","2009-08-31",null,"2009-08-31",{"$nulls":5},6]
[7329,"Carneau béton pour transport d'air surpressé, groupe de travail ",1,"GR Group","Technique","TGC - DTI","2009-08-31",null,"2009-08-31",{"$nulls":5},6]
[7330,"Base de partage REX :  Inondation d'un poste de pompage suite à une fuite sur joint ",1,"GR Group","Technique","R&E","2009-09-02",null,"2009-09-02",{"$nulls":5},6]
[7332,"RAFT, regroupement des fp concernant le RAFT",1,"GR Group","Technique","DTI","2009-09-02",null,"2009-09-02",{"$nulls":5},3]
[7333," Automatisme - Test plateforme (domaine technique) ",2,"GR Group","Technique","DTG","2009-09-04","Regis LANCON","2009-09-04","2009-09-04",{"$nulls":4},12]
[7334,"Purchasing - Delayed suppliers deliveries  ",2,"GR Group","Processus",null,"2009-09-21","Damien CABEZAS","2009-09-21","2009-09-21",{"$nulls":4},6]
[7335,"Amélioration matrice des Risques et Opportunités  ",2,"GR Group","Processus",null,"2009-09-21","Cedric BARET","2009-09-21","2009-09-21",{"$nulls":4},6]
[7336,"Calcul de l'Exposition Nette sur Projet/Affaire ",2,"GR Group","Processus",null,"2009-09-23","Patrick THEROND","2009-09-23","2009-09-23",{"$nulls":4},6]
[7337,"Digester Heat Calculation ",4,"GR Group","Technique",null,"2009-10-01","Gregory GNOS","2009-09-30","2009-09-30","2009-10-01","2009-10-01",null,null,6]
[7338,"Base de partage REX : Ultrafiltration",2,"GR Group","Technique",null,"2009-09-30","Pascal CREANCIER","2009-09-30","2009-09-30",{"$nulls":4},3]
[7339,"Base de Partage REX : Changement des supports et du caillebotis métalliques par des résines  ",1,"GR Group","Technique",null,"2009-09-30",null,"2009-09-30",{"$nulls":5},3]
[7340,"Base de partage REX : Protection cathodique, longévité des anodes / Vida útil ánodos de sacrificio  ",1,"GR Group","Technique",null,"2009-09-30",null,"2009-09-30",{"$nulls":5},3]
[7341,"DIGECO : emploi de panneaux préfabriqués plans ",4,"GR Group","Technique",null,"2009-10-01","Denis MARCHAND","2009-09-30","2009-09-30","2009-10-01","2009-10-01",null,null,3]
[7342,"Base de partage REX : Mise en route pont racleur Densadegs ",1,"GR Group","Technique",null,"2009-09-30",null,"2009-09-30",{"$nulls":5},3]
[7343,"TEST1 DFA",4,"BU Degrémont France Assainissement","Technique",null,"2009-10-08","Marianne CLAVERIE","2009-10-08","2009-10-08","2009-10-08","2009-10-08",null,null,3]
[7345,"Osmose Inverse Tubes de Pression Sinistre de BARKA  ",1,"GR Group","Technique",null,"2009-10-08","Jean Luc MALIGE","2009-10-08",{"$nulls":5},3]
[{"$nulls":14},15]
[{"$nulls":14},12]
[{"$nulls":14},3]
[{"$nulls":14},3]
[{"$nulls":14},12]
[{"$nulls":14},6]
[{"$nulls":14},6]