{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["Graph","Graphikgrundlag. techn. Fortsch"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":5,"defined_names":37,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Graph","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Graphikgrundlag. techn. Fortsch","index":1,"n_rows":9,"n_cols":28,"rows_kept":9,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[]
[]
[]
[null,null,"2008-09-01","2008-10-01","2008-11-01","2008-12-01","2009-01-01","2009-02-01","2009-03-01","2009-04-01","2009-05-01","2009-06-01","2009-07-01","2009-08-01","2009-09-01","2009-10-01","2009-11-01","2009-12-01","2010-01-01","2010-02-01","2010-03-01","2010-04-01","2010-05-01","2010-06-01","2010-07-01","2010-08-01","2010-09-01","2010-10-01"]
[null,"Techn. FS IST (kum.)",0.06,0.08,0.08,0.09,0.09,0.1324,0.1483,0.2742,0.2941,0.3669,0.3851,0.3984,0.504,0.504,0.504,0.5027,0.5027,0.5192,0.5192,0.5389]
[null,"Techn. FS SOLL gem. Terminplan (kum.)",0.10802576451995259,0.1687298854207823,0.24365475701303835,0.293496594231529,0.3518997945476096,0.4144118451205057,0.46953472145397074,0.5155007388384037,0.5681671315685499,0.57360431054919,0.6762925760568945,0.7335640102726195,0.8146656979693075,0.8771236665349664,0.9087317265902806,0.9442907941525089,0.9679968391939945,1.0075069142631372,1.0351639668115369,1.066772026866851,1.1164164361912288,1.12]
[null,"Techn. FS SOLL Anbindung an GU (kum.)",{"$nulls":12},0.504,0.56,0.62,0.68,0.74,0.8,0.85,0.9,0.95,1,1,1,1,1]